## Task Tracker
Cooper FX System — New Requirements & Implementation Tracker
# | Requirement / Sub-task | Description | Status
Req 1 | Manual Invoice Selection in FX Form | User can manually choose which SAP invoices to consume instead of auto-FIFO only
1.1 | Available Invoices API | Returns invoices with remaining stock for a part number, sorted by FIFO | Completed
1.2 | Invoice Selection Modal UI | Interactive table with per-invoice qty input and real-time validation | Completed
1.3 | Backend Dual Mode Support | Auto-FIFO (default) when no selection provided, manual when user selects | Completed
1.4 | Impact Analysis | Confirmed zero breaking changes to existing reconciliation workflow | Completed
Req 2 | Part History Page | View complete transaction history (incoming + outgoing) for any part with running balance
2.1 | Part History Page | Merges incoming and outgoing transactions into single chronological timeline | Completed
2.2 | Running Balance | Running balance calculation across merged timeline (stock in - stock out) | Completed
2.3 | Customer Info Display | Customer Name and Code from InvoiceRetailPartMap and Invoice models | Completed
2.4 | Retail Invoice Number | Added retail invoice number in outgoing rows for traceability | Completed
Req 3 | Part History Excel Export | Export Part History data to Excel for single part or all parts
3.1 | Single-Part Export | Excel export endpoint with date range filtering (from/to date) | Completed
3.2 | All-Parts Export | Excel export covering every part in the system | Completed
3.3 | All Fields Included | Date, Type, Reference, Company, Customer Code, Qty, USD Rate, INR Rate, Balance | Completed
3.4 | Download Button | Download button on Part History page with date filter modal | Completed
Req 4 | Balance History Page | Invoice-level consumption history showing how each SAP invoice stock was consumed
4.1 | Balance History Page | Shows original invoice qty and each consumption event | Completed
4.2 | Running Balance | Running balance per invoice (starting qty to after each consumption) | Completed
4.3 | Null Safety Fixes | Fixed 500 errors on invoices with zero/null quantities | Completed
4.4 | Orphan Record Handling | Skip records with missing invoice entries | Completed
Req 5 | Stock Ledger Report (Excel) | Excel report: Opening Stock, Shipment, Despatch, Closing Stock grouped by customer
5.1 | Requirement Analysis | Mapped Excel columns to DB fields, identified data gaps | Completed
5.2 | Stock Ledger Backend | Opening Stock, Shipment, Despatch, Closing Stock calculations | Completed
5.3 | Styled Excel Output | Matching Cooper required column format with subtotals row | Completed
5.4 | Date Period Modal | This Month / This Year / All Time / Custom date range on Dashboard | Completed
Req 6 | Customer Name & Code Visibility | Show customer name and code in invoice listings and API responses
6.1 | Invoice List API | Added customer_name and customer_code to all-invoices serializer | Completed
6.2 | Part History Outgoing | Company name from InvoiceRetailPartMap for outgoing entries | Completed
6.3 | Part History Incoming | Customer name from Invoice model for incoming entries | Completed
Req 7 | Profit Calculation Formulas Correction | Audit and correct profit decomposition formulas
7.1 | Formula Audit | Audited selling_profit, fx_profit, profit_absolute, profit_fx_only | Completed
7.2 | Formula Verification | selling_profit = (sell_usd - buy_usd) x qty x fx_rate | Completed
7.3 | Edge Case Fixes | Division by zero in fc_rate_with_discount and rate_sale_from_wh_per_unit | Completed
7.4 | Formula Documentation | All formulas documented with variable definitions | Completed
Req 8 | Production Bug Fixes & Hardening | Fix crashes, null values, debug code in production
8.1 | to_decimal() Fix | Safely handles None, empty strings, invalid values (returns 0) | Completed
8.2 | .lower() Crash Fix | Fixed crash on None value in export_history endpoint | Completed
8.3 | Debug Cleanup | Removed all print() debug statements from production code | Completed
8.4 | Null Safety Guards | Consumption history loop guards for orphaned records and null usd_rate | Completed
Req 9 | Bulk FX Upload Feature | Upload Excel file to process multiple FX entries at once
9.1 | Template Download Endpoint | Styled Excel template with all required column headers | Completed
9.2 | Bulk Upload Endpoint | Each row processes independently with FIFO auto-selection | Completed
9.3 | Per-Row Validation | Missing fields, invalid numbers, duplicate invoices, insufficient stock | Completed
9.4 | Result Summary Modal | Dashboard modal: Total/Success/Failed counts + per-row error details | Completed
9.5 | Auto-Calculated Fields | INR rate = usd_rate x conversion_rate (server-side) | Completed
Req 10 | Docker Deployment Setup | Containerize application for production deployment
10.1 | Backend Dockerfile | Django backend with Python 3.11 and Gunicorn | Completed
10.2 | Frontend Dockerfile | React frontend with Node 20 and Nginx | Completed
10.3 | Docker Compose | Orchestrate both services with auto-restart | Completed
10.4 | Production Deployment | Deploy to production server | Pending
Req 11
11.1 | Dry Run API Endpoint | Parse Excel, compare with DB stock, and return validation JSON without saving | Pending
11.2 | Interactive Staging Grid | Editable UI table to show valid/invalid rows side-by-side with required stock | Pending
11.3 | Inline Error Correction | Allow users to fix typos directly in the browser and re-validate instantly | Pending
11.4 | Manual Invoice Override | Allow users to select specific wholesale invoices per row instead of automatic FIFO | Pending
11.5 | Atomic Batch Commit API | Save the entire batch securely to the database with transaction rollback for integrity | Pending
Summary
Total New Requirements | 11
Total Sub-tasks | 44
Completed Sub-tasks | 38
Pending Sub-tasks | 6
Pending Items
1 | Production deployment using Docker (Req 10.4) |  | Pending
2 | Interactive Bulk-Upload Staging Area (Req 11) |  | Pending
3 | Bug fixes reported during UAT / production testing |  | Pending
4 | Minor UI enhancements based on client feedback |  | Pending